## Guide
Help
1 | Go to REF tab and fill-in the various activities that are part of project
2 | In REF tab, define the various levels and associated costs
3 | Ensure that a list of resources and associated levels are pre-populated to allow for easy reference in Resource plan
4 | In ResourcePlan sheet, start selecting various activities and assign them to resource. Please note that you will have to assign activity to each resource individually at this time.
5 | Start populating the allocation for each week. All the allocations are specified as % and the filled value is automatically highlighted for quick validation.
6 | Fill the "Planned Duration" column with any other estimation provided for comparision purpose.
7 | Select the resources in the bottom half of the excel to identify whether the resources are leveled properly and not over/under-allocated across all the activities in a given week.
8 | Please note that excel has been created to support 50 Activities, resources, levels and about 100 allocations (activity - resource mappings). A majority of these rows are hidden.

## ResourcePlan
# | Activity | Resource | Planned Duration (Weeks) | Level | Price | Calculated Duration (Weeks) | Planned Cost | Calculated Cost | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28
1 | Account Relationship | AMGR1 | 2 | Account Mgr | 200 | 1.25 | 16000 | 10000 | Week 1: 15%; Week 2: 10%; Week 3: 10%; Week 4: 10%; Week 5: 10%; Week 6: 10%; Week 7: 10%; Week 8: 10%; Week 9: 10%; Week 10: 10%; Week 11: 10%; Week 12: 10%
2 | Project Management | PM1 | 4 | Project Mgr | 150 | 6.75 | 24000 | 40500 | Week 1: 100%; Week 2: 100%; Week 3: 50%; Week 4: 50%; Week 5: 25%; Week 6: 25%; Week 7: 25%; Week 8: 25%; Week 9: 25%; Week 10: 50%; Week 11: 100%; Week 12: 100%
3 | Requirement | TL1 | 3 | Technical Lead | 125 | 2.5 | 15000 | 12500 | Week 1: 100%; Week 2: 100%; Week 3: 25%; Week 4: 25%
4 | Requirement | SrD1 | 4 | Sr. Developer | 100 | 3.5 | 16000 | 14000 | Week 1: 100%; Week 2: 100%; Week 3: 100%; Week 4: 50%
5 | Design | TL1 | 2 | Technical Lead | 125 | 2 | 10000 | 10000 | Week 3: 75%; Week 4: 75%; Week 5: 50%
6 | Design | SrD1 | 3 | Sr. Developer | 100 | 2.5 | 12000 | 10000 | Week 4: 50%; Week 5: 100%; Week 6: 100%
7 | Development Module 1 | TL1 | 1 | Technical Lead | 125 | 1.75 | 5000 | 8750 | Week 5: 25%; Week 6: 50%; Week 7: 50%; Week 8: 50%
8 | Development Module 1 | Dev1 | 2 | Developer | 75 | 4 | 6000 | 12000 | Week 5: 100%; Week 6: 100%; Week 7: 100%; Week 8: 100%
9 | Development Module 2 | SrD1 | 2 | Sr. Developer | 100 | 2 | 8000 | 8000 | Week 7: 100%; Week 8: 100%
10 | Development Module 2 | Dev2 | 2 | Developer | 75 | 2 | 6000 | 6000 | Week 7: 100%; Week 8: 100%
11 | Integration Testing | TL1 | 3 | Technical Lead | 125 | 3 | 15000 | 15000 | Week 5: 50%; Week 6: 50%; Week 7: 50%; Week 8: 50%; Week 9: 50%; Week 10: 50%
12 | Integration Testing | Tester1 | 7 | Developer | 75 | 6 | 21000 | 18000 | Week 5: 100%; Week 6: 100%; Week 7: 100%; Week 8: 100%; Week 9: 100%; Week 10: 100%
13 | Integration Testing | Dev2 | 3 | Developer | 75 | 4 | 9000 | 12000 | Week 5: 100%; Week 6: 100%; Week 9: 100%; Week 10: 100%
14 | Production Deployment | Dev1 | 4 | Developer | 75 | 2 | 12000 | 6000 | Week 9: 100%; Week 10: 100%
15 | Production Deployment | SrD1 | 2 | Sr. Developer | 100 | 2 | 8000 | 8000 | Week 9: 100%; Week 10: 100%
16 | Production Deployment | TL1 | 2 | Technical Lead | 125 | 1 | 10000 | 5000 | Week 9: 50%; Week 10: 50%
17 | Support | SrD1 | 2 | Sr. Developer | 100 | 2 | 8000 | 8000 | Week 11: 100%; Week 12: 100%
18 | Support | Dev1 | 2 | Developer | 75 | 2 | 6000 | 6000 | Week 11: 100%; Week 12: 100%
Unhide
| Total |  | 50 |  |  | 50.25 | 207000 | 209750
Resource
|  | AMGR1 | [6 empty] | Week 1: 0.15; Week 2: 0.1; Week 3: 0.1; Week 4: 0.1; Week 5: 0.1; Week 6: 0.1; Week 7: 0.1; Week 8: 0.1; Week 9: 0.1; Week 10: 0.1; Week 11: 0.1; Week 12: 0.1
|  | PM1 | [6 empty] | Week 1: 1; Week 2: 1; Week 3: 0.5; Week 4: 0.5; Week 5: 0.25; Week 6: 0.25; Week 7: 0.25; Week 8: 0.25; Week 9: 0.25; Week 10: 0.5; Week 11: 1; Week 12: 1
|  | TL1 | [6 empty] | Week 1: 1; Week 2: 1; Week 3: 1; Week 4: 1; Week 5: 1.25; Week 6: 1; Week 7: 1; Week 8: 1; Week 9: 1; Week 10: 1
SrD1 | bar: Week 1 to Week 12
Dev1 | bar: Week 5 to Week 12
Dev2 | bar: Week 5 to Week 10
Tester1 | bar: Week 5 to Week 10
0
0
0
| Unhide for additional lines | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## REF
| Activities | Resources | Level | Level | Price (per hr)
| Account Relationship | AMGR1 | Account Mgr | Account Mgr | 200
| Requirement | PM1 | Project Mgr | Project Mgr | 150
| Design | TL1 | Technical Lead | Technical Lead | 125
| Development Module 1 | SrD1 | Sr. Developer | Sr. Developer | 100
| Development Module 2 | Dev1 | Developer | Developer | 75
| Integration Testing | Dev2 | Developer | Intern | 50
| Performance Testing | Tester1 | Developer
UAT
Production Deployment
Support
Project Management
Unhide to add additional items